## business plan
Business Plan
Summary
Name | Team Involved | Status | Dependent On | Priority | Timeline 1 - Start | Timeline 1 - End | Deadline | Budget | Documents | Notes
Define our Vision & Goals |  | Working on it |  | Critical | 2022-03-01 | 2022-03-06 | 2022-04-06 |  | https://monday.monday.com/docs/2301602988 | Add notes
Define Customer Needs |  | Done | Define our Vision & Goals | High | 2022-03-07 | 2022-03-10 | 2022-04-20 |  | https://monday.monday.com/docs/2301603588 | Add notes
[5 empty] | 2022-03-01 | 2022-03-10 | 2022-04-06 to 2022-04-20 | 0
Market Analysis
Name | Team Involved | Status | Dependent On | Priority | Timeline 1 - Start | Timeline 1 - End | Deadline | Budget | Documents | Notes
Assess market size & scope |  | Done | Research market | Medium | 2022-04-15 | 2022-04-22 | 2022-05-05 |  | https://monday.monday.com/docs/2301604310 | Add notes
[5 empty] | 2022-04-15 | 2022-04-22 | 2022-05-05 | 0
Marketing Plan
Name | Team Involved | Status | Dependent On | Priority | Timeline 1 - Start | Timeline 1 - End | Deadline | Budget | Documents | Notes
Brainstorm Core Marketing messages |  | Done |  | Medium | 2022-03-16 | 2022-03-31 | 2022-03-31 |  | https://monday.monday.com/docs/2332287269
[5 empty] | 2022-03-16 | 2022-03-31 | 2022-03-31 | 0
Competitive Analysis
Name | Team Involved | Status | Dependent On | Priority | Timeline 1 - Start | Timeline 1 - End | Deadline | Budget | Documents | Notes
Research market |  | Working on it | Define our Vision & Goals | High | 2022-04-07 | 2022-04-14 | 2022-05-04 | 5000 | https://monday.monday.com/docs/2301605664
[5 empty] | 2022-04-07 | 2022-04-14 | 2022-05-04 | 5000
Financial Projections
Name | Team Involved | Status | Dependent On | Priority | Timeline 1 - Start | Timeline 1 - End | Deadline | Budget | Documents | Notes
Establish price vs competition |  |  |  | Medium | 2022-04-26 | 2022-04-30 | 2022-04-30
[5 empty] | 2022-04-26 | 2022-04-30 | 2022-04-30 | 0