## single project
Single Project
Planning
Name | Subtasks | Owner | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Completion Date | Completion Status
Task 1 | Subtask 1, Subtask 2 |  | Done | 2023-05-01 | 2023-05-09 | 9 |  | 12 | 8 | 2023-05-02 | Done On Time ✅
Subitems | Name | Owner | Status | Due Date
Subtask 1
Subtask 2
Task 2 |  |  | Done | 2023-05-10 | 2023-05-18 | 9 | Task 1 | 22 | 20 | 2023-05-16 | Done On Time ✅
Task 3 |  |  | Done | 2023-05-19 | 2023-05-27 | 9 | Task 2 | 10 | 14 | 2024-01-09 | Done Late ☑️
Milestone- Planning |  |  | Done | 2023-05-28 | 2023-05-28 | 0 | Task 3 |  |  | 2023-06-01 | Done Late ☑️
|  |  |  | 2023-05-01 | 2023-05-28 | 27 |  | 44 | 42 | 2023-05-02 to 2024-01-09 | null
Execution
Name | Subtasks | Owner | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Completion Date | Completion Status
Task 4 |  |  | Working on it | 2023-05-29 | 2023-06-06 | 9 | Milestone- Planning | 30 | 30
Task 5 |  |  | Future steps | 2023-06-07 | 2023-06-22 | 16 | Task 4 | 9 | 10
Task 6 |  |  | Future steps | 2023-06-23 | 2023-07-01 | 9 | Task 5 | 13 | 10
Milestone - Execution |  |  | Future steps | 2023-07-02 | 2023-07-02 | 0 | Task 6
|  |  |  | 2023-05-29 | 2023-07-02 | 34 |  | 52 | 50 |  | null
Launch
Name | Subtasks | Owner | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Completion Date | Completion Status
Task 7 |  |  | Future steps | 2023-07-03 | 2023-07-11 | 9 | Milestone - Execution | 5 | 5
Task 8 |  |  | Future steps | 2023-07-12 | 2023-07-20 | 9 | Task 7 | 6 | 3
Task 9 |  |  | Future steps | 2023-07-21 | 2023-07-29 | 9 | Task 8 | 12 | 16
Milestone - Launch |  |  | Future steps | 2023-07-30 | 2023-07-30 | 0 | Task 9
|  |  |  | 2023-07-03 | 2023-07-30 | 27 |  | 23 | 24 |  | null