## project workflow
Project Workflow
Initation
Name | Owner | Description | Priority | Timeline - Start | Timeline - End | Duration | Deadline | Status | Dependent On | Budget | Deliverables
BCA Board |  | Add details | High | 2022-04-01 | 2022-04-08 | 8 | 2022-05-07 | Complete |  | 50 | https://monday.monday.com/docs/7032180362
Project Charter |  | Add details | Low | 2022-04-07 | 2022-04-14 | 8 | 2022-05-05 | Complete |  | 0 | https://monday.monday.com/docs/7032180415
Stakeholder Analysis |  | Add details | Medium | 2022-04-22 | 2022-04-29 | 8 | 2022-05-10 | Working on it | Project Charter | 0 | https://monday.monday.com/docs/7032180445
|  |  |  | 2022-04-01 | 2022-04-29 |  | 2022-05-05 to 2022-05-10
Planning
Name | Owner | Description | Priority | Timeline - Start | Timeline - End | Duration | Deadline | Status | Dependent On | Budget | Deliverables
Pre kickoff Meeting |  | Add details | Medium | 2022-05-05 | 2022-05-12 | 8 | 2022-05-31 | Not started |  | 0
Project Cost Plan |  | Add details | Low | 2022-05-13 | 2022-05-20 | 8 | 2022-05-31 | Working on it | Pre kickoff Meeting | 0 | https://monday.monday.com/docs/7032180627
Kick Off Meeting |  | Add details | Medium | 2022-05-21 | 2022-05-22 | 2 | 2022-05-31 | Working on it | Project Cost Plan | 50 | https://monday.monday.com/docs/7032180587
|  |  |  | 2022-05-05 | 2022-05-22 |  | 2022-05-31
Execution
Name | Owner | Description | Priority | Timeline - Start | Timeline - End | Duration | Deadline | Status | Dependent On | Budget | Deliverables
Direct Project Plan (WBS) |  | Add details | Medium | 2022-06-02 | 2022-06-03 | 2 | 2022-06-30 | Not started |  | 0 | https://monday.monday.com/docs/7032180478
Monitor Quality |  | Add details | Medium | 2022-06-04 | 2022-06-05 | 2 | 2022-06-30 | Not started | Direct Project Plan (WBS) | 0 | https://monday.monday.com/docs/7032180552
|  |  |  | 2022-06-02 | 2022-06-05 |  | 2022-06-30